## Sheet1
S/N | Task/Milestone | Status | 2021-08-04 | 2021-08-05 | 2021-08-06 | 2021-08-07 | 2021-08-08 | 2021-08-09 | 2021-08-10 | 2021-08-11 | 2021-08-12 | 2021-08-13
1 | Kickoff meeting to finalize project choice and clarify project scope and deliverables | Completed | All
2 | Meetings
2.1 | Share initial findings and create work breakdown structure | Completed |  |  | All
2.2 | Progress update | [7 empty] | All
3 | Define problem statement and draft introduction | Completed |  |  | Ash
4 | Data Preparation
4.1 | Check and remove duplicate rows | Completed |  |  | Ray & Joey
4.2 | Check for and replace 'M', '-', 'T', ' ' values in affected columns appropriately | Completed |  |  | Ray & Joey
4.3 | Visualize distribution of trap location and define cutoff latitude | Completed |  |  | Ray & Joey
4.4 | Assign weather station and associated variables to trap location based on corresponding latitude | Completed |  |  | Ray & Joey
4.5 | Sum number of mosquitoes for rows with the exact same date, species, trap, latitude, longitude, & wnv in trap dataset | Completed |  |  | Ray & Joey
4.5 | Engineer and create 'Relative Humidity', 'Day', 'Week', 'Month' and 'Year' variables | Completed |  |  | Ray & Joey
4.6 | Drop irrelevant columns and final check for any missing value | Completed |  |  | Ray & Joey
4.7 | Export cleaned datasets | Completed |  |  | Ray & Joey
4.8 | Create Data Dictionary for each dataset | Completed |  |  | Ray & Joey
5 | Exploratory Data Analysis
5.1 | Descriptive statistics | Completed | [5 empty] | Joey & Ray
5.2 | Target variable visualization | Completed | [5 empty] | Joey & Ray
5.3 | Categorical variable visualization | Completed | [5 empty] | Joey & Ray
5.4 | Numerical variable visualization | Completed | [5 empty] | Joey & Ray
5.5 | Cross variable visualization | Completed | [5 empty] | Joey & Ray
5.6 | Feature-target variable visualization | Completed | [5 empty] | Joey & Ray
5.7 | Time series visualization of weather variables | Completed | [5 empty] | Joey & Ray
5.8 | Geographical visualization of trap and spray locations | Completed | [5 empty] | Joey & Ray
6 | Modelling workflow
6.1 | Plot heatmap of correlation matrix for numerical variables in each dataset | Completed | [5 empty] | Tim
6.2 | Create features matrix and target vector | Completed | [5 empty] | Tim
6.3 | train-test split and scale X_train | Completed | [5 empty] | Tim
6.3 | Create, instantiate and fit the following classification models - Logistic Regression, K-Nearest Neighbour, Random Forest Classifier and Linear Support Vector Machine | Completed | [5 empty] | Tim
6.4 | Compare and evaluate models using evaluation metrics | Completed | [5 empty] | Tim
6.5 | Analyze top predictors of selected model | Completed | [5 empty] | Tim
6.6 | Make predictions for Kaggle dataset and submit predictions on Kaggle | Completed | [5 empty] | Tim
7 | Cost-Benefit Analysis
7.1 | Research and define costs and benefits | Completed | [5 empty] | Ash
7.2 | Estimate benefits by computing short-term and long-term direct and indirect costs | Completed | [5 empty] | Ash
7.3 | Estimate maximum cost of spraying pesticides | Completed | [5 empty] | Ash
7.4 | Perform cost-benefit anaylsis | Completed | [5 empty] | Ash
8 | Draft recommendations and conclusion | Completed | [5 empty] | Ash
9 | Collate and integrate different project parts | Completed | [7 empty] | Joey
10 | Presentation
10.1 | Prepare indivdiual presentation slides | Completed | [8 empty] | All
10.2 | Compile individual presentation slides | Completed | [8 empty] | All
10.3 | Rehearsal and feedback | Completed | [8 empty] | All
10.4 | Review, finalize and submit slides | Completed | [8 empty] | All
10.5 | Presentation day | Completed | [9 empty] | All